## Journal
Apprenti.e | Jonathan Junod |  | Durée total (h ou p) |  | 24p
Classe ou Groupe | Mid2A / GRP2C |  | Experts |  | -
Chef.fe de Projet | Olivera Kobi S. |  | Bulle / Domaine / Module |  | INF / DEV / P_Prod
Sujet | Craft Me Up, un jeu en winforms pour les portes ouvertes
Tâches | Dates | Durées [min] | Explications | Etats | Date de fin | Sources, liens, références, commits …
Setup | 2025-11-03 | 30 | setting up the work environnement | Finished | 14:10 | https://github.com/Jonathan150408/Craft-Me-Up
Explanations |  | 35 | Explanations of the code for me | Finished | 14:45
Class diagram |  | 45 | Creating a diagram for the code's classes | Finished | 15:45 | https://eduvaud-my.sharepoint.com/:u:/r/personal/pb62kjx_eduvaud_ch/_layouts/15/Doc.aspx?sourcedoc=%7B5BF0A89E-E3A6-4CD4-BA7E-BFDC17A68BD3%7D&file=P_CraftMeUp_ClassDiagram.vsdx&fromShare=true&action=default&mobileredirect=true
Bilan du jour : | Jour 1 | Durée totale: | 110
Class diagram | 2025-11-09 | 30 | Creating a new version of the classes diagram | Finished | 16:20 | Work at home
Bilan du jour : | Jour 2 | Durée totale: | 30
Debating | 2025-11-10 | 45 | Debating about the code optimization | Finished | 13:55
Github project |  | 5 | Adding a kanban to github | Finished | 14:05 | https://github.com/users/Jonathan150408/projects/4/views/1
CdC |  | 10 | Read and complete the CdC written by Neo | Finished | 14:15
Coding |  | 50 | Correcting the obstacle class | Finished | 15:45
Git-problem |  | 25 | Solving a problem with the github project issues | Finished | 14:45 | https://github.com/users/Jonathan150408/projects/6/views/1
Bilan du jour : | Jour 3 | Durée totale: | 135
Class diagram | 2025-11-17 | 15 | Updating the classes diagram | Finished | 13:25
Coding |  | 105 | Optimizing Shoot me up | Finished | 15:20
Coding |  | 25 | Correcting Shoot me up | Finished | 15:25
Bilan du jour : | Jour 4 | Durée totale: | 145
Coding | 2025-11-24 | 40 | trying to understand why the number of frame per second isn't always the same | Finished | 13:10 | https://chatgpt.com/
Searching |  | 80 | Trying to understand how the display can work without pictureboxes | Finished | 13:50
coding |  | 5 | correcting the framerate issue | Finished | 15:20
Coding |  | 20 | Implementing the new random wave generation | Finished | 15:45
Bilan du jour : | Jour 5 | Durée totale: | 145
Coding | 2025-12-01 | 35 | Implementing the random wave generation system | Finished | 13:45
Coding |  | 105 | trying to fix the memory leak | Finished | 15:45 | https://chatgpt.com/
Bilan du jour : | Jour 6 | Durée totale: | 140
absent | 2025-12-08 | 25 | I was supposed to go to Sebeillon but actually not | Finished | 8:25
installation |  | 35 | Installing visual studio 2026 | Finished | 9:00
Coding |  | 25 | implementing the bosses waves for later (no bosses now) | Finished | 9:25
Coding |  | 45 | Implementing the pause menu | Finished | 10:25
Coding |  | 15 | fixing the broken wave generation | Finished | 10:40
Bilan du jour : | Jour 7 | Durée totale: | 145
installation | 2025-12-15 | 5 | Installing visual studio 2026 om the usual pc | Finished | 13:15
Evaluation |  | 25 | Making the evaluation of my project with M. Mveng | Finished | 13:40
Correcting |  | 45 | Correcting the rapport of my mysql project | Finished | 14:25
Debating |  | 35 | Waiting fr Neo to be done, helping him | Finished | 15:15
Coding |  | 30 | Implementing the pause menu | Finished | 15:45
Bilan du jour : | Jour 8 | Durée totale: | 140
Configuring | 2026-01-05 | 85 | Installing Visual studio 2026 on a VM | Finished | 14:35
Coding |  | 35 | Implementing the new spawning rules | Finished | 15:25
Testing |  | 20 | Testing the 2 new features with 500 sequeletons | Finished | 15:45
Bilan du jour : | Jour 9 | Durée totale: | 140
Bilan du jour : | Jour 10 | Durée totale: | 0
Total en heures |  | 16.6
Si nécessaire, [ Copier ] & [ Insérer ] un ou des jours supplémentaires avant la ligne du total

## Restrictions
Finished | Finished late | In the work | Not started