## Journal
Apprentice | Néo Darbellay |  | Total duration (in periods of 45 minutes) |  | 56p
Class/Group | CID2A/GRP2C |  | Experts |  | -
Project Manager(s) | S. Oliveira, G. Bianco and A. Gugler |  | Bubble / Domain / Module |  | INF / DEV / P_Prod
Subject | Craft Me Up
Task | Dates | Durations | Explanations | States | End time | Sources, links, references, commits …
Setup | 2025-11-03 | 30 | Setting up the work environment | Finished | 14:10 | https://github.com/Jonathan150408/Craft-Me-Up
Explanations |  | 35 | Explanation of the code | Finished | 14:45
Class diagram |  | 60 | Creating a diagram for every class | Not finished | 15:45 | Not everything is done, will be finished next session
Daily review: | Day 1 | Total duration: | 125
Class diagram | 2025-11-04 | 30 | Finishing the class diagrams | Finished | 8:45
Writing |  | 50 | Writing the product specifications | Finished | 9:35 | This may get changed later, as this was done without Jonathan's approval, as he wasn't there
Backlog |  | 25 | Writing 4 new issues | Finished | 10:15 | This was done in a .txt file originally, as the GitHub Project wasn't set up yet and I cannot create it
Designing |  | 35 | Designing 4 images for the new issues | Finished | 10:50
Coding |  | 35 | Started working on the code optimization | Not finished | 11:25 | Not everything is done, will be finished next session
Daily review: | Day 2 | Total duration: | 175
Debating | 2025-11-10 | 45 | Debating on code optimization | Finished | 13:55 | This was used for the new class diagrams
Backlog |  | 55 | Writing the fifth issue & adding the previous ones to GitHub Project | Finished | 15:10 | This took a while, as GitHub decided to disable issues in the project.
Coding |  | 45 | Continuing code optimization | Finished | 15:55 | All progress here has been reset as the PC's power source got turned off by a classmate.
Daily review: | Day 3 | Total duration: | 145
Other | 2025-11-11 |  | Working on a presentation for another class | Finished | 9:25 | I'm not adding the duration, as this wasn't part of the project. However, it did take up some of the allocated project time. I'll take time off during a weekend to compensate for it.
Coding |  | 105 | Continuing code optimization | Finished | 11:25 | Character.cs, Projectile.cs, Obstacle.cs
Daily review: | Day 4 | Total duration: | 105
Coding | 2025-11-17 | 105 | Continuing code optimization | Finished | 15:10 | Enemy.cs, along with fixes for Character, Projectile and Obstacle.
Coding |  | 10 | Analyzing the code to see if I missed anything that could be optimized | Finished | 15:20
Coding |  | 25 | Implementing Jonathan's optimisation | Finished | 15:45 | Still needs some fixing
Daily review: | Day 5 | Total duration: | 140
Coding | 2025-11-18 | 100 | Fixing rendering issues with the new system | Finished | 10:30 | Since the optimization was so big, a lot of things broke and had to be changed There are still some issues, but I'll need Jonathan to help out
Coding |  | 45 | Fixing projectiles with the new system | Finished | 11:15 | They shoot again, but have some issues that will need more fixing
Coding |  | 10 | Re-adding health bar visuals (obstacle, characters) | Finished | 11:25
Daily review: | Day 6 | Total duration: | 155
Coding | 2025-11-24 | 10 | Fixing an issue with zombies teleporting to 0 0 | Finished | 13:20
Coding |  | 20 | Testing the old app to see if it was easier to fix than the current one | Finished | 13:40 | V1 used DrawImage instead of Picturebox, which isn't as resource-heavy.
Coding |  | 30 | Re-implementing the old CFrame system | Finished | 14:10
Coding |  | 15 | Adapting Obstacle to work with the new CFrame system | Finished | 14:25
Coding |  | 10 | Adapting Character to work with the new CFrame system | Finished | 14:35
Coding |  | 10 | Adapting Enemy to work with the new CFrame system | Finished | 14:45
Coding |  | 30 | Adapting Projectile to work with the new CFrame system | Finished | 15:30
Backlog |  | 5 | Writing 1 new issue | Finished | 15:35
Designing |  | 10 | Designing an image for the new issue | Not finished | 15:45 | Will finish it tomorrow
Daily review: | Day 7 | Total duration: | 140
Designing | 2025-11-25 | 15 | Continuation of the new issue's design | Finished | 8:15
Coding |  | 175 | Adapting the main program to work with the new CFrame system | Not finished | 11:25 | This took a while, as there was a big memory leak to fix. I also made the camera follow the player during that time. This is not finished yet.
Daily review: | Day 8 | Total duration: | 190
Coding | 2025-12-01 | 140 | Fixing the memory leak | Not finished | 15:45 | Still not done, but I got an idea, which is to do a using(Bitmap Sprite = GetSprite(Type)) instead of storing a sprite for each entity
Daily review: | Day 9 | Total duration: | 140
Coding | 2025-12-02 | 45 | Fixing the memory leak | Finished | 8:45
Images/Coding |  | 75 | Getting better sprites, and renaming them in the code | Finished | 10:15
Coding |  | 15 | Re-adding health bar visuals (obstacle, characters) and creating a better GenerateWaves() | Finished | 10:30
Coding |  | 10 | Creating better collisions | Finished | 10:40
Coding |  | 10 | Implemented a background image to the game | Finished | 10:50
Setup |  | 35 | Setting up the presentation PC | Finished | 11:25
Daily review: | Day 10 | Total duration: | 190
Preparation | 2025-12-08 | 60 | Preparing today's PC | Finished | 9:00 | I had issues with this, as Visual Studio 2022 wasn't, and couldn't, be installed, so we had to result in trying to use VSC, then installing VS2026
Designing |  | 15 | Designing an image for the new issue | Finished | 9:15
Coding |  | 65 | Creating new enemy types | Not finished | 10:35 | Implemented the wither, but not any other (didn't have time)
Daily review: | Day 11 | Total duration: | 140
Preparation | 2025-12-15 | 15 | Downloading VS2026 on the current PC | Finished | 13:25 | Since we upgraded the project to .NET 10.0, we had to upgrade VS2022 to VS2026
Coding |  | 125 | Creating new boss types | Not finished | 15:45 | I also optimized the code, so that enemies only store one lastCooldown variable in case they can shoot
Daily review: | Day 12 | Total duration: | 140
Preparation | 2025-12-16 | 60 | Downloading VS2026 on a VM | Finished | 9:00 | This too longer than expected, as I had some issues getting the right permissions and had to make a virtual machine instead
Coding |  | 10 | Adding sprites to the new boss types and making them work | Finished | 9:10
Coding |  | 45 | Making some bosses ignore obstacles | Finished | 10:10
Coding |  | 65 | Fixing the pause button issues | Finished | 11:25 | I also implemented DeltaTime movement
Daily review: | Day 13 | Total duration: | 180
Preparation | 2026-01-05 | 10 | Fixing some technical issues | Finished | 13:15
Coding |  | 10 | Reviewing the code | Finished | 13:25
Designing |  | 10 | Adding heart sprites to the game | Finished | 13:35
Coding |  | 45 | Fixing issues regarding enemy spawning and enemy shooting | Finished | 14:20
Coding |  | 70 | Making the skeletons smarter | Finished | 15:45 | https://github.com/Jonathan150408/Craft-Me-Up/issues/7
Daily review: | Day 14 | Total duration: | 145
Coding | 2026-01-20 | 135 | Implementing the pseudo-random map | Finished | 10:30 | I made it so that isntead of being a grid of 8x8 chunks of 8x8 tiles, it's 16x16 chunks of 16x16 tiles, as that looked better
Backlog |  | 5 | Writing 2 new issues (#9 and #10) | Finished | 10:35
Coding |  | 40 | Implementing game window scale | Finished | 11:10
Coding |  | 15 | Working on the biomes | Not finished | 11:25
Daily review: | Day 15 | Total duration: | 195
Coding | 2026-01-27 | 15 | Working on the biomes | Finished | 8:15
Coding |  | 25 | Fixing an issue with camera clamping causing an error | Finished | 8:45 | There are some issues to fix with zooming out causing lag, but that will be fixed later
Coding |  | 10 | Fixing the main menu scale | Finished | 8:55
Coding |  | 65 | Implementing the settings | Finished | 10:15 | So far, only GAMESPEED has a setting, but that'll change later on.
Coding |  | 15 | Making the settings save | Finished | 10:30
Coding |  | 40 | Fixing some render-based lag | Finished | 11:10
Coding |  | 15 | Changing how biomes render | Finished | 11:25
Coding |  | 25 | Adding a setting to update the chunk amount | Finished | 14:45 | Finished a test early, so I worked on this
Coding |  | 5 | Fixed obstacle generation | Finished | 15:20
Daily review: | Day 16 | Total duration: | 215
Coding | 2026-02-10 | 10 | Fixed multiple small issues | Finished | 8:10 | Issues such as render order and conditional logic failing
Coding |  | 55 | Changed how enemy health renders | Finished | 9:05
Coding |  | 40 | Changed how player stats render | Finished | 10:00
Coding |  | 85 | Fixed some rendering issues | Not finished | 11:25 | Reduced rendering lag as much as I could for today You can now start the game with 128x128 chunks, but it is incredibly laggy
Daily review: | Day 17 | Total duration: | 190
Coding | 2026-03-03 | 105 | Optimized the code even more | Not finished | 10:00 | Made it so that after a certain level of zoom, obstacles turn into solid color images and used a few code shortcuts to make it way cleaner
Coding |  | 85 | More optimization | Not finished | 11:25 | Tried to get rid of "TextHelpers", but it ended up creating more issues than anything. Next step is to cache
Daily review: | Day 18 | Total duration: | 190
Coding | 2026-03-17 | 55 | Final rendering optimization | Finished | 10:00 | I noticed that there were issues with obstacle collisions, as there was no way to get nearby obstacles, so everything looped through every obstacle
Coding |  | 35 | Final memory optimization and V2 release | Finished | 10:35 | I believe the game is finally V2-Ready
Daily review: | Day 19 | Total duration: | 90
Total time spent (in hours) |  | 49.8

## Restrictions
Finished | Not finished | In the work | Not started