## Journal
Apprenti.e | Néo Darbellay |  | Durée total (h ou p) |  | 32p
Classe ou Groupe | CID2A/GRP2C |  | Experts |  | -
Chef.fe de Projet | PPT |  | Bulle / Domaine / Module |  | Dev / Programmer orienté objet / 320
Sujet | P_POO - Shoot Me Up
Tâches | Dates | Durées [min] | Explications | Etats | Date de fin | Sources, liens, références, commits …
Analysis | 2025-09-29 | 25 | Reading the specifications (CDC) and learning how GitHub Projects work | Finished | 12:50
Creation |  | 20 | Creating the GitHub Project and repo, along with updating the .NET framework | Finished | 13:10 | https://github.com/users/neo-darbellay/projects/1/ https://github.com/neo-darbellay/P_POO-I320/
Creation |  | 10 | Creating the VS project | Finished | 13:20
Report |  | 35 | Start of the report (rapport) | Finished | 13:55
Backlog |  | 15 | Creation of Issue #1 in the backlog | Finished | 14:10 | This issue (#1) concerns player movement
Illustration |  | 35 | Illustration and finalization of Issue #1 | Finished | 14:45
Bilan du jour : | Jour 1 | Durée totale: | 140
Backlog | 2025-09-30 | 10 | Creation of Issue #2 in the backlog | Finished | 13:25 | This issue (#2) concerns obstacles
Illustration |  | 10 | Illustration of Issue #1 | Finished | 13:35
Coding |  | 95 | Implementation of Issue #1 using the Base given by the teacher | Finished | 15:25
Coding |  | 15 | Modifying the game area to have a border | Finished | 15:40
Coding |  | 105 | Implementation of Issue #2 to the program | Finished | 17:25 | It doesn't fully work, needs some patching
Bilan du jour : | Jour 2 | Durée totale: | 235
Coding | 2025-10-06 | 10 | Addition of a "type" variable for Characters and Obstacles so they can be rendered with different sprites | Finished | 10:55
Fixing |  | 20 | Modification of Issue #2's implementation to make it work | Finished | 11:15
Coding |  | 15 | Temporary implementation of Issue #3 to the program to test issue #2 | Finished | 11:30 | This implementation isn't final, as the code relies on individual key presses, instead of key combinations. Issue #3 will be created right after this
Backlog |  | 10 | Creation of Issue #3 in the backlog | Finished | 11:40
Illustration |  | 10 | Illustration of Issue #3 | Finished | 11:50
Coding |  | 25 | Implementation of Issue #3 to the program | Finished | 11:15
Backlog |  | 15 | Creation of Issue #4 | Finished | 13:25
Illustration |  | 20 | Illustration of Issue #4 | Finished | 13:45
Backlog |  | 5 | Creation of Issue #5 | Finished | 13:50
Illustration |  | 5 | Illustration of Issue #5 | Finished | 13:55
Backlog |  | 5 | Creation of Issue #6 | Finished | 14:00
Illustration |  | 10 | Illustration of Issue #6 | Finished | 14:10
Backlog |  | 5 | Creation of Issue #7 | Finished | 14:15
Illustration |  | 15 | Illustration of Issue #7 | Finished | 14:30 | I stopped midway through the illustration to help a classmate out
Backlog |  | 5 | Creation of Issue #8 | Finished | 14:35
Illustration |  | 10 | Illustration of Issue #8 | Finished | 14:45 | Some issues are still missing, but will be added later
Bilan du jour : | Jour 3 | Durée totale: | 185
Backlog | 2025-10-07 | 10 | Creation of Issue #9 | Finished | 13:20
Illustration |  | 5 | Illustration of issue #9 | Finished | 13:25
Backlog |  | 5 | Creation of Issue #10 | Finished | 13:30
Illustration |  | 5 | Illustration of issue #10 | Finished | 13:35
Report |  | 10 | Updating the report | Finished | 13:45
Coding |  | 140 | Implementation of issue #4 to the program | Finished | 16:20
Coding - Extra |  | 10 | Implementation of a cooldown for shooting | Finished | 16:30
Analysis |  | 15 | Analysis of the git convention in place | Finished | 16:45
Install |  | 10 | Installation of Github Desktop | Finished | 16:55 | Created a commit to add every file to GitHub
Coding |  | 25 | Implementation of Issue #5 to the program | Finished | 17:20 | Not done
Github Desktop |  | 5 | Committing everything to GitHub | Finished | 17:25
Bilan du jour : | Jour 4 | Durée totale: | 235
Coding | 2025-10-24 | 70 | Implementation of Issue #5 to the program | Finished | 16:40 | Took a small break and started again at 17:05
Coding |  | 85 | Implementation of Issue #6 to the program | Finished | 18:30
Coding |  | 170 | Implementation of Issue #8 to the program | Finished | 21:50 | Took a 30 minute break in between to go eat
Bilan du jour : | Jour 5 | Durée totale: | 325
Setup | 2025-10-27 | 20 | Downloading VS and Github Desktop again | Finished | 11:00 | The class computers got changed
Coding |  | 50 | Fixed small issues and tweaked with some variables | Finished | 11:50
Coding |  | 125 | Implementation of the base terrain | Finished | 14:45
Bilan du jour : | Jour 6 | Durée totale: | 195
Coding | 2025-10-28 | 25 | Implementation of Issue #9 to the program | Finished | 13:35
Coding |  | 20 | Changed the constructors of multiple classes so that Object creation is easier | Finished | 13:55
Coding |  | 50 | Implementation of Issue #10 to the program | Finished | 14:45
Coding |  | 30 | Creation of new enemy types for issue #7 | Finished | 15:30
Coding |  | 30 | Fixed small issues with map position | Finished | 16:00
Coding |  | 35 | Implementation of Issue #7 to the program | Finished | 16:35
Bilan du jour : | Jour 7 | Durée totale: | 190
Bilan du jour : | Jour 8 | Durée totale: | 0
Total en heures |  | 25.2
Si nécessaire, [ Copier ] & [ Insérer ] un ou des jours supplémentaires avant la ligne du total

## Restrictions (hidden)
Finished | Finished (late) | In the work | Not started